## Example
Project Name | Statistical Command Interface (sci)
Project Description | a statistics tool that can analyze data in various ways, provide visualizations of the data in various forms, and flexibly integrate new modules of function as needed or developed
Modules | Milestone | Due Date | Goal % Complete | Actual % Complete | Test & Expected Result | Received Result | Deliverable ( in addition to this form, updated)
I. Command Line Environment | 1. Write introductory text | 2019-09-20 | 100% | 100% | prints the introductory text | expected | screenshot of output
"core" module | 2. Code for prompt and text input | 2019-09-20 | 100% | 100% | displays the prompt "sci.core > " and prints out any line entered | expected | screenshot of output
| 3. Create class that represents a command/module | 2019-09-27 | 100% | 100% | the rest of the program works as described | n/a | nothing
| 4. Code exit function | 2019-09-27 | 100% | 100% | when the command 'exit' is entered, the program exits | expected | screenshot of output
| 5. Create class that represents a help message | 2019-09-27 | 100% | 100% | See box below | expected | screenshot of output
| 6. Code first help function | 2019-09-27 | 100% | 100% | when the command 'help' is entered and the current module is core, the help message with the modules is printed; when 'help' + a module name is entered (or the current module is not core), the help message for the module is printed; when 'help' + a command name is entered, the help message for the command is entered | expected | screenshot of output
II. Data Entry Module | 1. Create object to represent the module | 2019-10-04 | 100% | 100% | when the command 'data' is entered, the prompt changes to "sci.data > " and the current module string variable changes to "data" and for development only is then printed | expected | screenshot of output
| 2. Add functionality to enter quantitative data in the console | 2019-10-04 | 100% | 100% | when 'add list1' is entered, the program prompts for the data with "> " and when "3.5 2 3 5.6 7" is entered into the new prompt, the data is stored in list1 and for development only "3.5 2 3 5.6 7" is output | expected | screenshot of output
| 3. Add functionality to import quantitative data from a file | 2019-10-04 | 100% | 100% | when 'import c:\users\fostecar000\file.txt list1' is input on Windows and that file has "3.5 2 3 5.6 7" in it, the program will output a success message (storing the data in list1) and for development only output "3.5 2 3 5.6 7" | expected | screenshot of output
| 4. Add functionality to enter categorical data in the console | 2019-10-04 | 100% | 100% | when '\add catlist1' is entered, the program prompts for the data with "> " and when "(male cat) (female dog)" is entered, the data is stored in catlist1 and for development only "(male cat) (female dog)" is output | expected | screenshot of output
| 5. Add functionality to import categorical data from a file | 2019-10-04 | 100% | 100% | when '\import c:\users\fostecar000\file.txt catlist1' in input on Windows and that file contains "(male cat) (female dog)", the data is stored in catlist1 and for development only "(male cat) (female dog)" is output | expected | screenshot of output
III. Analysis Module | 1. Create object to represent the module | 2019-10-11 | 100% | 100% | when the command 'analyze' is entered, the prompt changes to "sci.analysis > " and the current module string variable changes to "analysis" and for development only is then printed | expected | screenshot of output
| 2. Add commands for each statistic: sample mean, median, IQR, Q1, Q3, min, max, population/sample standard deviation, number of entries, mode, and sum | 2019-10-18 | 100% | 100% | after "3.5 2 3 5.6 7" is entered into list1, the commands "xbar list1", "xtilde list1", "iqr list1", "q1 list1", "q3 list1", "min list1", "max list1", "lsigma list1", "s list1", "n list1", "mode list1", and "usigma list1" will produce the outputs of 4.22, 3.5, 3.8, 2.5, 6.3, 2, 7, about 1.82, about 2.04, 5, "2 3 3.5 5.6 7", and 21.1 respectively; after "(male 3.5) (female 2) (female 3) (male 5.6) (female 7)" is input into catlist1, the output of "\xbar catlist1 2", "\xtilde catlist1 2", etc. should match the above outputs. | expected | screenshot of output
| 3. Add general supercommands: five number summary, distribution | 2019-10-18 | 100% | 100% | after "3.5 2 3 5.6 7" is entered into list1, the commands "fivenum list1" and "dist list1" will produce "min: 2 q1: 2.5 xtilde: 3.5 q3: 6.3 max: 7" and "center: 3.5 spread: 3.8"; after "(male 3.5) (female 2) (female 3) (male 5.6) (female 7)" is entered into catlist1, the commands "\fivenum catlist1 2" and "\dist catlist1 2" should produce the above output | expected | screenshot of output
IV. Graphing Module | 1. Create object to represent the module | 2019-10-25 | 100% | 100% | when the command 'graph' is entered, the prompt changes to "sci.graphing > " and the current module string variable changes to "graphing" and for development only is then printed | expected | screenshot of output
| 2. build framework for graphics window | 2019-10-25 | 100% | 100% | when the test program is run, a window should be shown when 'show' is entered and be hidden when 'hide' is entered | expected | screenshot of output
| 3. implement bar chart | 2019-11-01 | 100% | 100% | after "(male 3.5) (female 2) (female 3) (male 5.6) (female 7)" is entered into catlist1, the command '\bar catlist1 1' should prompt the user for the label of the x axis with "X-Axis Label > " and then "Title > ". when "Gender" and "Gender of 5 Subjects" is entered, a bar graph in a small GUI window should appear, with two bars on the x axis, which is labeled "Gender": "male" and "female", with 2 in the "male" bar and 3 in the "female" bar, and titled "Gender of 5 Subjects" | expected | screenshot of output
| 4. implement pie chart | 2019-11-08 | 100% | 100% | after "(male 3.5) (female 2) (female 3) (male 5.6) (female 7)" is entered into catlist1, the command '\pie catlist1 1' should prompt for more information with "Title > ". when "Gender of 5 Subjects" is entered, a small GUI window should appear with a pie chart, with the title "Gender of 5 Subjects" and 40% = male and 60% = female | expected | screenshot of output
| 5. implement histograms | 2019-11-15 | 100% | 100% | after"(male 3.5) (female 2) (female 3) (male 5.6) (female 7)" is entered into catlist1 or "3.5 2 3 5.6 7" is entered into list1 and the command "\hist catlist1 2" or "hist list1" is entered, the program should prompt the user with "Title > ", "Y-Axis Title > ", "X Minimum (enter = auto) > ", "X Step (enter = auto) > ". after "Average Pencil Length (in)", "Number of people", "0", and "2" are entered, a small GUI window with a histogram titled "Average Pencil Length (in)" should appear, with a y axis of "Number of people", and 3 bars, 2-4 (with 3 in it), 4-6 (with 1 in it), and 6-8 (with 1 in it) | expected | screenshot of output
| 6. implement boxplots | 2019-11-22 | 100% | 100% | after "(male 3.5) (female 2) (female 3) (male 5.6) (female 7)" is entered into catlist1 or "3.5 2 3 5.6 7" is entered into list1 and the command "\box catlist1 2" or "box list1" is entered, the program should prompt the user with "Title > ". after "Average Pencil Length (in)" is entered, a small GUI window with a boxplot titled "Average Pencil Length (in)" should appear, with a boxplot representing the 5 number summary of the data (see five number summary milestone in analysis) | expected | screenshot of output
| 7. implement saving images to files | 2019-12-06 | 100% | 100% | after "(male 3.5) (female 2) (female 3) (male 5.6) (female 7)" is entered into catlist1, the command "save \bar catlist1 1 output.png" should prompt the user as above and save the bar chart to output.png. after "3.5 2 3 5.6 7" is entered into list1, the command "save hist list1 output.png" should prompt the user as above and the save the histogram to output.png | expected | screenshot of output
V. Additional Work | 1. Create parser for mathematical expressions | 2019-12-06 | 50% | 60% | See below | expected | screenshot of output
|  | 2019-12-13 | 100% | 100%
| a. Code extendable lexer | 2019-12-06 | 100% | 100% | when '3 * 4 + <usigma list1>' is entered, for development only, the token list "3", "*", "4", "+", and "<usigma list1>" should be printed | expected | screenshot of output
| b. Code parser that creates AST | 2019-12-06 | 50% | 75% | when '3 * 4 + <usigma list1>' is entered, for development only, a string representing the tree + * usigma list1 3 4 should be printed | expected | screenshot of output
|  | 2019-12-13 | 100% | 100%
| c. Create interpreter for AST | 2019-12-13 | 100% | 100% | when '3 * 4 + usigma list1' is entered and list1 is "3.5 2 3 5.6 7", the program should print 33.1 | expected | screenshot of output
| 2. Add additional commands/supercommands (Optional) | 2019-12-13 | 100% | n/a | TBD (Optional) |  | screenshot of output
| 3. Add additional functionality (Optional) | 2019-12-13 | 100% | n/a | 0 of one type for bar graphs? TBD (Optional) |  | screenshot of output
December 13th = due date
sep 20 (9/20/2019)
2019-09-27
oct 4 (10/4/2019)
2019-10-11
2019-10-18
2019-10-25
nov 1 (11/1/2019)
2019-11-08
2019-11-15
2019-11-22
2019-11-29
dec 6 (12/6/2019)
2019-12-13